## 26-0052
BOCC APPROVAL SEPTEMBER 2, 2026
BOARD OF BIDS AND CONTRACTS AUGUST 27, 2026
2. PUBLIC ELEVATOR UPGRADES IN MAIN COURTHOUSE -- PROJECT SERVICES
FUNDING -- PROJECT SERVICES
(Request sent to 158 vendors)
RFB #26-0052 Contract
| Icon Structures, Inc.* | Otis Elevator Company
Lump Sum, Base Bid | 1274447 | 1789400
Days to Substantial Completion | 358 | 650
Days to Final Completion | 7 | 30
Total Calendar Days | 365 | 680
Bid Bond | Yes | Yes
Acknowledged Addendum | Yes | Yes
No Bid | Abba Construction LLC | Bathquest Wichita, Inc.
| Key Construction, Inc. | Murray & Sons Construction Co., Inc.
On the recommendation of Joe Thomas, on behalf of Project Services, Corey Stokes moved to accept the negotiated bid from Icon Structures, Inc. in the amount of $1,274,447.00. Brandi Baily seconded the motion. The motion passed unanimously.
This project is to modernize and replace equipment for three (3) traction elevators in the Main Courthouse. The three (3) elevators to be replaced are the south elevator bank in the main lobby.
These elevators are in desperate need of repairs. Out of the six (6) lobby elevators, one (1) is currently down and being used for parts to keep the remaining five (5) operational. New elevator equipment will be installed in the machine room on the Penthouse Mezzanine above Floor 12.
All old equipment being replaced will be removed and used as stock for other compatible elevators until a future modernization occurs. Elevator cab is to remain and select interior finishes are to be updated such as new controls and wall panels.
To minimize disruption, the modernization will be staggered so that elevator service always remains available to building occupants. Phase 1 will include elevators 5 and 6 and Phase 2 will include elevator 4.
Notes:
*The original bid amount from Icon Structures, Inc. was $1,363,247.00. Negotiations were conducted by Project Services with Icon Structures, Inc. to value engineer a reduction in overall cost, with the above results.
Funding was still needed after negotiations, so a CIP Amendment for this increase was submitted to the Board of County Commissioners and approved on Wednesday, August 19, 2026.
Questions and Answers
Brandi Baily: I guess I do have one. So this is replacing the south bank elevators but we say that one is currently down. The one currently down is that the south bank elevator or is that a north bank elevator? So we'll have three (3) down at one time essentially?
Sandy Anguelov: Yes. It's elevator five (5), which is the center one that is down right now. It's been down for a while.
Brandi Baily: So at any given point in time, there'll be two (2) elevators down essentially?
Sandy Anguelov: Correct.
Tania Cole: I know Andrew gave an extensive presentation to the Commissioners last week.